## Deliverable Summary
Product/Service Launch Deliverables Tracker
MAJOR MILESTONES | Due Date |  |  |  |  | Status Key
Ideal Customer Profile Approved | Date | M1 | [5 empty] | In Process - High risk, roadblocked
Release X (launch feature complete) | Date | M2 | [5 empty] | In Process - delayed but action plan in place
Release X to Early Adoptors | Date | M3 | [5 empty] | In Process - On Schedule
Messaging Tested & Approved | Date | M4 | [5 empty] | Completed
Internal Readiness (Support & Sales Trained) | Date | M5
Website Live | Date | M6
Press Announcement Approved | Date | M7 |  |  |  | 250 | Days to Launch!
Deliverables |  | Owner Initials | % Com. | Dependancy | Milestone | Due Date | Status | Notes
Aim
Ideal Customer Profile & Market Sizing | INSERT LEAD FOR THIS SECTION
| Define long-term potential user base |  |  |  | M1
| Define ideal customer profile (ICP) for launch |  |  |  | M1 |  |  | This is a very critical step, as it will determine who you test messages against, who you train sales to target, who is recruited to beta test your product/service offering, and how you prioritize product requirements.
| Size based on first targeted segement & total opportunity (# of users, potential revenue) |  |  |  | M1
| Identify target list of accounts |  |  |  | M1 |  |  | This is the list of accounts for which you are building the launch version of your product, not everyone you may sell to over time.
Competitive Analysis | INSERT LEAD FOR THIS SECTION
| Identify the competitive landscape | [6 empty] | Identify all alternative approaches to solving the problem your solution addresses
| Complete SWOT analysis | [6 empty] | Identify competitive approaches strengths & weaknesses. This will be the basis for differentiator messaging so be honest with yourself.
| Identify 2-4 differentiators you will prioritize | [6 empty] | Differentiators must be unique, something you can prove & IMPORTANT to the buyer. Buyers don't always know what they want so be sure your market research tests your hypotheses not just want users say they want.
Persona Development | INSERT LEAD FOR THIS SECTION
Identify all members of the buying committee at your ICP
Conduct qualitative interviews
Document buyer's journey stages for your product/service
| Document buyer personas | [6 empty] | Personas provide essential guidance to those developing your product/service offering and will provide the foundation for sales training down the road.
MVP Product Requirements | INSERT LEAD FOR THIS SECTION | [6 empty] | In this section you will track progress against the development of validated minimum viable product requirements. This is the list of capabilities that you must have prior to launch, not everything you will build over time.
Survey ICP sample
| Prototype demo | [6 empty] | In the case of a service offering the prototype may be a detailed description of the services to be performed.
Focus group
Influencers | INSERT LEAD FOR THIS SECTION
| Establish Advisory Board | [6 empty] | Even if you don't formally launch and advisory board you need to identify key influencers early in your development process so they can feel a part of your product design.
Monthly Communications Plan
Association Memberships
Ready
Development | INSERT LEAD FOR THIS SECTION
X launch feature complete release
X early adoptor release
X general availability ready
Help documentation
Messaging | INSERT LEAD FOR THIS SECTION
| Draft messaging framework | [6 empty] | Be sure to include product description, benefits, features/capabilties, differentiators & elevator pitches by persona
| Message testing | [6 empty] | Don't skimp here. You need to validate messages with real buyers in your ICP.
Launch messages approved
Branding | INSERT LEAD FOR THIS SECTION
Trademark key terms
Logo Treatment
Product Name
| Brand Guide/Color Palette | [6 empty] | If not already established as part of a broader company brand.
URL purchase program
Screen Saver/Home Screen
Iconography library
Pricing | INSERT LEAD FOR THIS SECTION
| Costs documented | [6 empty] | Don't forget to document your actual costs - both cost to serve and anticipated cost to sell. Even if profitability is not your priority at launch you need to understand the implications on your business.
Competitive pricing collected
| Business impact models | [6 empty] | Pricing has a huge impact on the speed of market adoption and also profitability. Be sure to map out a variety of scenarios for the management team to consider.
Early adoptor pricing set
Price list approved
Sales Tools | INSERT LEAD FOR THIS SECTION
Value Calculator
Product Overview
Sales Presentation Business
Sales Presentation Technical
Message Map Poster/Quick Reference Guide
Thought-Leadership Manifesto/Whitepaper
How it works whitepaper
Why ICP cares whitepaper
Datasheet (describe offering specs)
FAQ Document
Post-release Roadmap Slide
Demo Script
Competitive battlecards
Analysts | INSERT LEAD FOR THIS SECTION
Analyst Briefing Calendar
Analyst Presentation
Monthly Communications Plan
Website | INSERT LEAD FOR THIS SECTION
| Designer/programmer selected | [6 empty] | This may be done internally by your own resources or you may hire an external agency to support the efforts.
Site architecture defined
Concepts Approved
Wireframes/Site Map Approved
Text Approved
Early adoptor success stories
Service/Product Overview
Search optimization plan (includes keywords)
Early Adoptor Program | INSERT LEAD FOR THIS SECTION
Project owner identified
Participants identified
| Applicant request form | [6 empty] | If you are actively seeking additional participants in your early adopter program make sure an online application form is easily found.
Participant contracts signed/recruited
Communications plan executed
Secure reference approvals
Finance/Legal | INSERT LEAD FOR THIS SECTION
License Agreement
Trademarks - Registration
Warranty written
Patent Applications Filed
Partners | INSERT LEAD FOR THIS SECTION | [6 empty] | This section is particulary important to mature businesses launching a new product or into a new segment. If partnerships have not yet been established or are not part of your business plan you can remove this section. However, before you do make sure there aren't complimentary providers worth leveraging as part of your efforts.
Program Outline
Program Brochure
Recruitment Presentation
Key Partner Briefings
Partner Training Scheduled
Sell
Sales Infrastructure Readiness | INSERT LEAD FOR THIS SECTION
Outbound office voice mail
800# for inquires
inbound email alias
Sales trained
| Target Contact List | [6 empty] | Be sure to include phone number & email address at a minimum. Mailing address & social profiles are helpful additions.
Introductory letters (persona based)
Call script tested (persona based)
Company training (non-sales) | INSERT LEAD FOR THIS SECTION
Support team trained (messaging & technical)
Services Team trained
Partners trained
Operations & Support Infrastructure Readiness | INSERT LEAD FOR THIS SECTION
Support Plan (Domestic & International)
CRM Tool Selected (including customer portal)
CRM Tool Live
Demo Accounts Set Up (Internal)
Demo content uploaded
Support Contract
Order & fufilment processes tested
Launch event | INSERT LEAD FOR THIS SECTION
Event strategy approved
Sponsorship/Space Agreement Signed
Graphics ordered
Demo
Staffing
Staff Shirts
Promo Materials
Give Away Items
Guest speakers
Invitations
Space plan
Public Relations | INSERT LEAD FOR THIS SECTION
Agency Selected
Agency contract signed
Kick Off Meeting Hosted
Media Training
Byline Article Strategy
Product Press Release
Press Tour Scheduled
Quote Sheet
Customer References
Partner References
Speaking Abstracts
Speaking Calendar
Target Awards List Identified
Advertising | INSERT LEAD FOR THIS SECTION
Ad Creative
Placement Contracts
Google Ad Words
Social channels | INSERT LEAD FOR THIS SECTION
Follower strategy approved
Social channels established
Editorial calendar set
Launch announcement content approved
Launch support messages prepared for key influencers
Launch support messages shared with employeess
Nurture Program | INSERT LEAD FOR THIS SECTION
Email Nurture Strategy
Launch emails written
3-5 touch drive to meeting email series
Note on J16: Samantha Stone: Red: Significant roadblock, needs escalation, effecting milestone schedule Yellow: Caution. May impact milestone schedule. Plan to address in place. Green: On schedule.
Note on B4: Customize these milestones to match your organizations naming convensions and needs just be sure to keep them at a strategic level.
Note on I11: Modify Launch Date on the countown calcultor tab to match your target launch. The countdown will automatically recalculate for you.
Note on E16: Each line item should be assigned an owner. A single person may be responsible for multiple actions but be sure not to overload any one individual with too many tasks.
Note on D18: For each section of deliverables assign a lead. This person does not have to do everything on the to-do list but it is their job to make sure it is happening and to track progress against those tasks.
Note on D24: For each section of deliverables assign a lead. This person does not have to do everything on the to-do list but it is their job to make sure it is happening and to track progress against those tasks.

## Countdown Calculator
Launch Date
250 | 2017-04-15
Note on C3: Insert your target launch date here.